## README
Last Update | 2019-04-22
Author | Thomas Lee Alex Shin Damian Turner David Huecker Matthew Coyne
Email | tlee066@ucr.edu wshin007@ucr.edu dturn003@ucr.edu mcoyn001@ucr.edu dh001@ucr.edu
Description | This is a SCRUM template designed for the Split project for CS180 Spring 2019
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
1 | Registration, Login/Logout | As an new user I want to be register for an account so I can login/logout of my account | 3 | 2
2 | Delete Account | As a registered user who is not interested in using the app anymore, I want to permanently delete my account. | 1 | 12
3 | Total Owed | As a forgetful user I want to see the total money amount that I currently owe to everyone. | 2 | 3
4 | Profile | As a user I want to be able to edit my profile to let others find me easier. (Name, picture, city, etc.) | 2 | 11
5 | Recents | As a frequent user I want to be able to see the users I’ve recently interacted with. | 4 | 6
12 | Request | As a registered user I want to be able to send requests to other users. | 10 | 1
6 | Search | As a registered user I want to be able to search for other users. | 2 | 4
7 | Group Request | As a registered user I want to be able to send/request multiple users notifications instead one at a time. (Create groups) | 6 | 9
8 | History | As a registered user I would like to pull up the history of my payments for the last 6-12 months | 2 | 10
9 | Notification | As a money concerned user I want to send email notifications to people you’ve requested from to remind them. | 2 | 5
10 | Tags/Categories | As a registered user I want to have my bills broken down into separate categories so I can see how I’m spending my money, or which users I send the most to. | 4 | 8
11 | Notes/Memo | As a forgetful user I want to be able to make notes on my payments so I can see what I’m paying for later. | 2 | 7
| Total |  | 32

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Get Total Owed from database (David)
Pull up all requests for user (Thomas)
Account creation and authentication with firebase (Alex Shin)
User database in firebase with email as primary key (Mathew)
Open and Close requests (Damian Turner)
Assign opened requests a unique id (Damian Turner)
Refine UI page, so all pages are linked/accesible (Alex)
Display current user in UI (David)
Display total owed in UI (Thomas)

## Archives
Sprint ID | Scrum Master | Tasks Completed
1 |  | Task 1: Start Database (Damian Turner)
1 |  | Task 6: Account Creation UI (David Hucker)
1 |  | Task 2: Account Creation (Thomas Lee)
1 |  | Task 3: Account Login/Logout (Thomas Lee/Alex Shin)
1 |  | Task 4: Create Request UI (Matthew Coyne)
1 |  | Task 5: "Create Request" database update (Damian Turner)